## Communications Plan Template
Communications Plan
Project Name:
Communications Plan - Client Name/Project Name
Audience | Message/Purpose | Content | Channel | Frequency | Next Date | Sender | Status | Feedback Mechanism
Name of Project Phase
Activity Group
Audience for the communication | e.g.Awareness, Acceptance, Engagement, Committment | Details to be included in the content of the message | e.g. Meeting, Conference Call, eMail, Letter | e.g. One Time, As Required, Daily, Weekly, Monthly, Quarterly, Yearly | Date of next communication | Person responsible for delivering the message |  | How targets will be able to provide feedback on the content

## Communications Plan - example
Stakeholder Communications Plan - Client Name/Project Name
Audience | Message/Purpose | Content | Channel | Frequency | Next Date | Sender | Status | Feedback Mechanism
Diagnose and Explore Phase
Kick off Project and Begin As-Is Assessment
Sponsor | Commitment | Project launch, start date, project plan & approach | Meeting | Once off | 2010-09-01 | Insert initials here….. | Completed
All Impacted Employees | Awareness | Project Overview | Newsletter | TBD |  |  | In progress
Project Team | Awareness & invitation to project launch | Invitation to the project launch | Invitation card | Once off
Accenture team | Planning | Project plan, roles & responsibilities, expectations | Meeting | Ongoing
Project Team, Sponsor | Project Introduction | Project introduction, approach, plan, data gathering & launch | Meeting | Once off
Sponsor | Invitation | Reinforce invitation | Voice Mail/Tel | Once off |  |  |  | Attendance confirmation
Project Team | Encourage participation & commitment | Welcome to the project, and encourage commitment | Memo | Once off
Project Team | Project Introduction | Kick off meeting, project plan, approach, launch & data gathering | Presentation | Once off
Accenture team | Team Induction | Project introduction (plan & approach), data gathering, communication plan, structure, roles & responsibilities, expectations & team building | Presentation | Once off
All employees involved in project (data gatherers, interviewers, etc.) | Launch project awareness & understanding | Project launch: introduction, background, objectives, scope, benefits, approach, & data gathering | Presentation | Once off
All Impacted Employees | Awareness | Project overview, approach, benefits & participation | Newsletter | TBD
Project Team | Co-operation during data gathering | Data gathering process, rationale for interviews & questionnaires, encourage co-operation | Memo | Once off
Project Team | Data gathering | Sampling Interviewees | Telephone | Ongoing
Core Project team | Team Induction | Invitation to Core Team Induction | Memo | Once off
Core Project team | Core Project team Induction | Project introduction (plan & approach), team introduction, data gathering process & team building | Presentations/Work session | Once off
Project Team | Data gathering | Gather information, build buy in, identify key issues | Interviews | Once off |  |  |  | Interviews sheets
Sample of employees | Data gathering | Distribute questionnaires to gather information, build buy in, & identify key issues | Questionnaires | Once off |  |  |  | Completed questionnaires
Core Project team | Project Team Update | Update, data request | Meeting | As required
Respondents | Data gathering | Return of questionnaires | Internal mail (questionnaires) | Once off |  |  |  | Completed questionnaires
Core Project team | Project Update | Status Update | Meeting | Weekly
Project Team | Project Update | Data Request | Meeting | Once off
Accenture Team | Data Gathering | Issue consolidation | Workshop | Once off
Project Team | Project Update | Status Update | Meeting | Weekly
Project Team | Data Gathering | Gather information , build buy in, identify key issues | Interviews | Once off |  |  |  | Interviews sheets
Core Project team | Data Request | Assess status of data request, identify problems, suggestions. | Work session | Once off
Sponsor | Project Update | Sponsor Report | Report | Once off
Sponsor | Project Update/ Commitment | Interviews & questionnaire findings and areas for further analysis | Presentation | Once off
Sponsor, Core Project Team | Project Overview & status | Status update, relationship building, buy-in, soliciting feedback, issues & concerns | One-on-one Meetings | Ongoing
Sponsor | Project Update | Status update, buy-in, soliciting feedback, issues & concerns | Presentation | As required
Sponsor | Project Update | Top Management Report | Report | Once off
All Impacted Employees | Awareness, updates & building support | Project overview & Status, upcoming events | Newsletter | Once off
Wrap Up Opportunity Identification
Project Team | Baseline Findings Presentation | Status Update, discussion of findings | Meeting | Weekly
Sponsor | Project Update | Status update, buy-in, soliciting feedback, issues & concerns | Presentation | As required
Sponsor | Baseline Findings Briefing | Findings on data received, analysis thereof and next steps | Meeting | Once off
Sponsor | Baseline Findings Presentation | Status update, discussion of findings | Meeting | Fortnightly
Core Project team | Project Status | Status Update | Meeting | As required
Data Gatherers | Thank you letter | Thank you for support during Data Gathering | Letter | Once off
Present Final Recommendations
Sponsor | Commitment & Ownership | Final presentation of findings, business architecture, logistics strategy & implementation plan | Presentation | Once off
Core Project team | Project round up meeting | Consolidation & Feedback | Meeting | Once off
Sample of employees | Data gathering on project awareness | Project awareness & effectiveness of Communication | Telephone survey | Once off
Review Board | Final Status Update | Final presentation of findings, business architecture, logistics strategy & implementation plan | Final Report | Once off
All Impacted Employees | Final Status Update | High level presentation of project deliverables | Newsletter | Once off

## Stakeholder Communication
Stakeholder Communication Plan Risk Mitigation
Concerns/Fears | Risks | Mitigation
Lack of strategic information and decisions taken | Stakeholders feel that information is kept away from them and that decisions are imposed | - Clearly communicate benefits and strategy of project - Communicate on a timely basis and give opportunity for feedback
Feedback is not listened to | Stakeholders feel that they are not taken seriously | - Generate two way communication which enables continuous improvement - Communicate results on feedback, address concerns
Overload of non-audience specific information | Stakeholders will ignore/not notice when a important message is being conveyed | - Communicate user specific information - Use specific channels for important messages
Messages are too complicated | Messages are no longer read by stakeholders | - Use simple, clear wording (no "consultant-ese" or technical jargon) - Tailor messages to audience - Offer support and opportunity for feedback - Demonstrate new concepts, terminology and processes
Overflow and boredom of written messages | Messages are no longer read by stakeholders | - Acid Test: is there a more beneficial way of communicating this message ? - Use multiple channels for the same stakeholders
“False" positive messages | Expectations are incorrectly set, stakeholders are confused/disappointed | - Communicate realistic, open messages - Communicate success stories and failures
Not clear how their daily job will be/is impacted | Stakeholders are frustrated and exhibit negative behaviors towards change | - Develop awareness of change and provide support - Show link to business needs - Promote intiatives, explain benefits and clearly communicate changes (positive and negative)